## Project Macherla
Dakansy-Macherla
| Select a period to highlight at right. A legend describing the charting follows. | [8 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
S.NO. | ACTIVITY | QUANTITY | UNIT | PLANNED START | PLANNED DURATION | PLANNED FINISH | ACTUAL START | ACTUAL DURATION | ACTUAL FINISH | PERCENT COMPLETE | PERIODS
 | time axis 2026-04-05 to 2026-06-06
PRELIMINARY WORKS
1 | Site Leveling and Grading | 8 | Acres | 2026-04-05 | 5 | 2026-04-10
2 | Construction of Boundary Wall | 1000 | Mtrs | 2026-04-08 | 6 | 2026-04-14
3 | PROCUREMENT - DELIVERY DATES
4 | PV Modules | 2.4 | MWp | 2026-03-10 | 65 | 2026-05-14
5 | Inverters | 8 | Nos | 2026-04-15 | 10 | 2026-04-25
| MMS Columns | 880 | Nos | 2026-03-10 | 40 | 2026-04-19
| MMS Super Structure | 76 | Tables | 2026-04-15 | 25 | 2026-05-10
6 | LT Panel | 1 | No | 2026-04-15 | 30 | 2026-05-15
7 | IDT | 1 | No | 2026-04-15 | 30 | 2026-05-15
8 | HT Panel | 1 | No | 2026-04-15 | 45 | 2026-05-30
9 | DC Cables | 1 | Lot | 2026-04-15 | 5 | 2026-04-20
10 | LT Cables | 1 | Lot | 2026-04-15 | 5 | 2026-04-20
11 | HT Cables | 1 | Lot | 2026-04-15 | 5 | 2026-04-20
12 | Aux System | 1 | Lot | 2026-04-15 | 35 | 2026-05-20
13 | Earthing and Lightning Material | 1 | Lot | 2026-04-15 | 30 | 2026-05-15
14 | MMS AND MODULE ERECTION WORKS
15 | Marking and Drilling | 880 | Nos | 2026-04-10 | 10 | 2026-04-20 | 2026-04-13 | 9 | 2026-04-22
16 | Concreting and Column Erection | 880 | Nos | 2026-04-20 | 10 | 2026-04-30
17 | Structure Erection | 76 | Tables | 2026-05-11 | 10 | 2026-05-21
19 | Module Erection | 76 | Tables | 2026-05-14 | 10 | 2026-05-24
20 | Modules Alignment and Tightening | 76 | Tables | 2026-05-24 | 5 | 2026-05-29
21 | DC WORKS
22 | Module Stringing | 76 | Tables | 2026-05-25 | 2 | 2026-05-27
23 | Erection of Inverters | 8 | Nos | 2026-05-01 | 2 | 2026-05-03
24 | Trench Excavation - AC/ DC Cable | 1 | Lot | 2026-04-30 | 4 | 2026-05-04
25 | DC Cabling | 8 | Lots | 2026-05-04 | 3 | 2026-05-07
26 | DC Terminations to Inverters | 8 | Sets | 2026-05-08 | 3 | 2026-05-11
28 | DC Earthing Works | 2.4 | MW | 2026-05-05 | 6 | 2026-05-11
29 | INVERTER TO LT PANEL
30 | Laying of INV-LT Cables | 8 | Lots | 2026-05-08 | 1 | 2026-05-09
31 | AC Terminations at Inverter | 8 | Nos | 2026-05-09 | 1 | 2026-05-10
32 | Inverter Earthing | 8 | Nos | 2026-05-10 | 1 | 2026-05-11
33 | LT PANEL
34 | Foundation for LT Panel | 1 | No | 2026-04-25 | 10 | 2026-05-05
35 | Erection of LT Panel | 1 | No | 2026-05-15 | 1 | 2026-05-16
36 | INV- LT Cables Termination | 8 | Lots | 2026-05-16 | 1 | 2026-05-17
37 | Laying of Control and Communication Cables | 1 | Lot | 2026-05-17 | 2 | 2026-05-19
38 | Aux System Installation | 1 | Lot | 2026-05-20 | 2 | 2026-05-22
39 | LT Panel Earthing | 1 | Lot | 2026-05-19 | 1 | 2026-05-20
41 | LT PANEL TO TRANSFORMER
42 | Transformer Foundation | 1 | No | 2026-04-25 | 10 | 2026-05-05
43 | Transformer Installation | 1 | No | 2026-05-15 | 1 | 2026-05-16
44 | Cable Tray LT - IDT | 1 | Lot | 2026-05-16 | 1 | 2026-05-17
45 | Cable Laying LT - IDT | 1 | Lot | 2026-05-17 | 1 | 2026-05-18
46 | Cable Terminations LT - IDT | 1 | Lot | 2026-05-18 | 1 | 2026-05-19
47 | Transformer Earthing | 1 | No | 2026-05-19 | 1 | 2026-05-20
48 | TRANSFORMER to HT PANEL
49 | HT Panel Foundation | 1 | No | 2026-04-25 | 10 | 2026-05-05
50 | HT Panel Installation | 1 | No | 2026-05-30 | 1 | 2026-05-31
51 | Cable Trench IDT - HT | 1 | Lot | 2026-05-31 | 1 | 2026-06-01
52 | Cable Laying IDT - HT | 1 | Lot | 2026-06-01 | 1 | 2026-06-02
53 | Cable Terminations IDT - HT | 1 | Lot | 2026-06-02 | 1 | 2026-06-03
54 | HT Yard Earthing | 1 | Lot | 2026-06-03 | 1 | 2026-06-04
55 | HT PANEL TO EVACUATION
56 | DP Structure Erection | 1 | No | 2026-04-26 | 2 | 2026-04-28
57 | Overhead Line Erection | 1 | Lot | 2026-04-28 | 7 | 2026-05-05
59 | Bay at Substation | 1 | No | 2026-05-05 | 20 | 2026-05-25
60 | HT Termination at Evacuation | 1 | Lot | 2026-05-25 | 1 | 2026-05-26
61 | Metering System Installation | 1 | Lot | 2026-05-26 | 1 | 2026-05-27
62 | Protection system Installation | 1 | Lot | 2026-05-27 | 1 | 2026-05-28
63 | HT Testing | 1 | No | 2026-05-28 | 1 | 2026-05-29
64 | Synchronization Readiness | 1 | No | 2026-05-29 | 1 | 2026-05-30
65 | SCADA AND COMMUNICATION
67 | Weather Station Installation | 1 | Lot | 2026-05-25 | 3 | 2026-05-28
66 | SCADA Installation | 1 | Lot | 2026-05-28 | 7 | 2026-06-04
68 | Communication Integration | 1 | Lot | 2026-06-04 | 4 | 2026-06-08
69 | EARTHING SYSTEM
70 | Earthing Grid Completion | 1 | Lot | 2026-05-15 | 6 | 2026-05-21
71 | Lightning Arrestor Installation | 1 | Lot | 2026-05-21 | 2 | 2026-05-23
72 | Earth resistance testing | 1 | Lot | 2026-05-23 | 1 | 2026-05-24
73 | TESTING AND COMMISSIONING
74 | Pre-commissioning checks | 1 | Lot | 2026-06-08 | 4 | 2026-06-12
77 | System Integration Testing | 1 | Lot | 2026-06-12 | 2 | 2026-06-14
78 | Final Commissioning | 1 | Lot | 2026-06-14 | 2 | 2026-06-16
Formulas:
PLANNED START = [PLANNED START, row above]+3
PLANNED START = MAX(([PLANNED START, row above]+1),(G11+1))
PLANNED FINISH = [PLANNED START]+[PLANNED DURATION]
ACTUAL FINISH = [ACTUAL START]+[ACTUAL DURATION]

## Project Sample (1)
ID | Name | Status | Duration | Baseline Duration | Baseline Work | Baseline Cost | Schedule Start Date | Baseline Start Date | Schedule End Date | Baseline Finish Date | Actual Start Date | Actual Finish Date | Forecasted Finish Date | Start Time | Finish Time | Actual Start Time | Actual Finish Time | Predecessors | Resources | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5
1 | PRELIMINARY WORKS | Not Started | 9days |  |  |  | 2026-05-04 | NA | 04/13/2026 | NA |  |  |  | 8:00 | 17:00
2 | Site Leveling and Grading | Not Started | 5days |  |  |  | 2026-05-04 | NA | 2026-09-04 | NA |  |  |  | 8:00 | 17:00
3 | Construction of Boundary Wall | Not Started | 6days |  |  |  | 2026-08-04 | NA | 04/13/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 2SS+3days
4 | PROCUREMENT - DELIVERY DATES | Not Started | 81days |  |  |  | 2026-11-03 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00
5 | PV Modules | Not Started | 65days |  |  |  | 2026-11-03 | NA | 05/14/2026 | NA |  |  |  | 8:00 | 17:00
6 | Inverters | Not Started | 10days |  |  |  | 04/16/2026 | NA | 04/25/2026 | NA |  |  |  | 8:00 | 17:00
7 | MMS Columns | Not Started | 40days |  |  |  | 2026-11-03 | NA | 04/19/2026 | NA |  |  |  | 8:00 | 17:00
8 | MMS Super Structure | Not Started | 25days |  |  |  | 04/16/2026 | NA | 2026-10-05 | NA |  |  |  | 8:00 | 17:00
9 | LT Panel | Not Started | 30days |  |  |  | 04/16/2026 | NA | 05/15/2026 | NA |  |  |  | 8:00 | 17:00
10 | IDT | Not Started | 30days |  |  |  | 04/16/2026 | NA | 05/15/2026 | NA |  |  |  | 8:00 | 17:00
11 | HT Panel | Not Started | 45days |  |  |  | 04/16/2026 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00
12 | DC Cables | Not Started | 5days |  |  |  | 04/16/2026 | NA | 04/20/2026 | NA |  |  |  | 8:00 | 17:00
13 | LT Cables | Not Started | 5days |  |  |  | 04/16/2026 | NA | 04/20/2026 | NA |  |  |  | 8:00 | 17:00
14 | HT Cables | Not Started | 5days |  |  |  | 04/16/2026 | NA | 04/20/2026 | NA |  |  |  | 8:00 | 17:00
15 | Aux System | Not Started | 35days |  |  |  | 04/16/2026 | NA | 05/20/2026 | NA |  |  |  | 8:00 | 17:00
16 | Earthing and Lightning Material | Not Started | 30days |  |  |  | 04/16/2026 | NA | 05/15/2026 | NA |  |  |  | 8:00 | 17:00
17 | MMS AND MODULE ERECTION WORKS | Not Started | 51days |  |  |  | 2026-10-04 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00
18 | Marking and Drilling | Not Started | 10days |  |  |  | 2026-10-04 | NA | 04/19/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 2
19 | Concreting and Column Erection | Not Started | 10days |  |  |  | 04/21/2026 | NA | 04/30/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 18SS+1day,7FS+1day
20 | Structure Erection | Not Started | 10days |  |  |  | 2026-12-05 | NA | 05/21/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 8FS+1day,19SS+5days
21 | Module Erection | Not Started | 10days |  |  |  | 05/16/2026 | NA | 05/25/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 5FS+1day,20SS+1day | 5FS
22 | Modules Alignment and Tightening | Not Started | 5days |  |  |  | 05/26/2026 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 21
23 | DC WORKS | Not Started | 28days |  |  |  | 2026-01-05 | NA | 05/28/2026 | NA |  |  |  | 8:00 | 17:00
24 | Module Stringing | Not Started | 2days |  |  |  | 05/27/2026 | NA | 05/28/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 21FS+1day
25 | Erection of Inverters | Not Started | 2days |  |  |  | 2026-02-05 | NA | 2026-03-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 19FS+1day,13 | 19FS+1day,6
26 | Trench Excavation - AC/ DC Cable | Not Started | 4days |  |  |  | 2026-01-05 | NA | 2026-04-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 19
27 | DC Cabling | Not Started | 3days |  |  |  | 2026-05-05 | NA | 2026-07-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 25FS+1day,12
28 | DC Terminations to Inverters | Not Started | 3days |  |  |  | 2026-09-05 | NA | 2026-11-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 27FS+1day
29 | DC Earthing Works | Not Started | 6days |  |  |  | 2026-06-05 | NA | 2026-11-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 26FS+1day
30 | INVERTER TO LT PANEL | Not Started | 4days |  |  |  | 2026-09-05 | NA | 2026-12-05 | NA |  |  |  | 8:00 | 17:00
31 | Laying of INV-LT Cables | Not Started | 1day |  |  |  | 2026-09-05 | NA | 2026-09-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 27FS+1day,13
32 | AC Terminations at Inverter | Not Started | 1day |  |  |  | 2026-11-05 | NA | 2026-11-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 31,28FF | 31
33 | Inverter Earthing | Not Started | 1day |  |  |  | 2026-12-05 | NA | 2026-12-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 32
34 | LT PANEL | Not Started | 27days |  |  |  | 04/26/2026 | NA | 05/22/2026 | NA |  |  |  | 8:00 | 17:00
35 | Foundation for LT Panel | Not Started | 10days |  |  |  | 04/26/2026 | NA | 2026-05-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 19SS+5days
36 | Erection of LT Panel | Not Started | 1day |  |  |  | 05/16/2026 | NA | 05/16/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 35FS+1day,9
37 | INV- LT Cables Termination | Not Started | 1day |  |  |  | 05/17/2026 | NA | 05/17/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 36,31 | 36
38 | Laying of Control and Communication Cables | Not Started | 2days |  |  |  | 05/18/2026 | NA | 05/19/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 37
39 | Aux System Installation | Not Started | 2days |  |  |  | 05/21/2026 | NA | 05/22/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 15,36
40 | LT Panel Earthing | Not Started | 1day |  |  |  | 05/20/2026 | NA | 05/20/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 38
41 | LT PANEL TO TRANSFORMER | Not Started | 25days |  |  |  | 04/26/2026 | NA | 05/20/2026 | NA |  |  |  | 8:00 | 17:00
42 | Transformer Foundation | Not Started | 10days |  |  |  | 04/26/2026 | NA | 2026-05-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 19SS+5days
43 | Transformer Installation | Not Started | 1day |  |  |  | 05/16/2026 | NA | 05/16/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 42FS+1day,10
44 | Cable Tray LT - IDT | Not Started | 1day |  |  |  | 05/17/2026 | NA | 05/17/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 43
45 | Cable Laying LT - IDT | Not Started | 1day |  |  |  | 05/18/2026 | NA | 05/18/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 44,13
46 | Cable Terminations LT - IDT | Not Started | 1day |  |  |  | 05/19/2026 | NA | 05/19/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 45
47 | Transformer Earthing | Not Started | 1day |  |  |  | 05/20/2026 | NA | 05/20/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 46
48 | TRANSFORMER to HT PANEL | Not Started | 40days |  |  |  | 04/26/2026 | NA | 2026-04-06 | NA |  |  |  | 8:00 | 17:00
49 | HT Panel Foundation | Not Started | 10days |  |  |  | 04/26/2026 | NA | 2026-05-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 19SS+5days
50 | HT Panel Installation | Not Started | 1day |  |  |  | 05/31/2026 | NA | 05/31/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 49FS+1day,11
51 | Cable Trench IDT - HT | Not Started | 1day |  |  |  | 2026-01-06 | NA | 2026-01-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 50
52 | Cable Laying IDT - HT | Not Started | 1day |  |  |  | 2026-02-06 | NA | 2026-02-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 51,14
53 | Cable Terminations IDT - HT | Not Started | 1day |  |  |  | 2026-03-06 | NA | 2026-03-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 52
54 | HT Yard Earthing | Not Started | 1day |  |  |  | 2026-04-06 | NA | 2026-04-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 53
55 | HT PANEL TO EVACUATION | Not Started | 34days |  |  |  | 04/27/2026 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00
56 | DP Structure Erection | Not Started | 2days |  |  |  | 04/27/2026 | NA | 04/28/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 49SS+1day
57 | Overhead Line Erection | Not Started | 7days |  |  |  | 04/29/2026 | NA | 2026-05-05 | NA |  |  |  | 8:00 | 17:00 |  |  | 56
58 | Bay at Substation | Not Started | 20days |  |  |  | 2026-06-05 | NA | 05/25/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 57
59 | HT Termination at Evacuation | Not Started | 1day |  |  |  | 05/26/2026 | NA | 05/26/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 58
60 | Metering System Installation | Not Started | 1day |  |  |  | 05/27/2026 | NA | 05/27/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 59
61 | Protection system Installation | Not Started | 1day |  |  |  | 05/28/2026 | NA | 05/28/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 60
62 | HT Testing | Not Started | 1day |  |  |  | 05/29/2026 | NA | 05/29/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 61
63 | Synchronization Readiness | Not Started | 1day |  |  |  | 05/30/2026 | NA | 05/30/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 62
64 | SCADA AND COMMUNICATION | Not Started | 14days |  |  |  | 05/26/2026 | NA | 2026-08-06 | NA |  |  |  | 8:00 | 17:00
65 | Weather Station Installation | Not Started | 3days |  |  |  | 05/26/2026 | NA | 05/28/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 58
66 | SCADA Installation | Not Started | 7days |  |  |  | 05/29/2026 | NA | 2026-04-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 65
67 | Communication Integration | Not Started | 4days |  |  |  | 2026-05-06 | NA | 2026-08-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 66
68 | EARTHING SYSTEM | Not Started | 9days |  |  |  | 05/16/2026 | NA | 05/24/2026 | NA |  |  |  | 8:00 | 17:00
69 | Earthing Grid Completion | Not Started | 6days |  |  |  | 05/16/2026 | NA | 05/21/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 16,26
70 | Lightning Arrestor Installation | Not Started | 2days |  |  |  | 05/22/2026 | NA | 05/23/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 69 | 69,16
71 | Earth resistance testing | Not Started | 1day |  |  |  | 05/24/2026 | NA | 05/24/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 70
72 | TESTING AND COMMISSIONING | Not Started | 8days |  |  |  | 2026-09-06 | NA | 06/16/2026 | NA |  |  |  | 8:00 | 17:00
73 | Pre-commissioning checks | Not Started | 4days |  |  |  | 2026-09-06 | NA | 2026-12-06 | NA |  |  |  | 8:00 | 17:00 |  |  | 67
74 | System Integration Testing | Not Started | 2days |  |  |  | 06/13/2026 | NA | 06/14/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 73
75 | Final Commissioning | Not Started | 2days |  |  |  | 06/15/2026 | NA | 06/16/2026 | NA |  |  |  | 8:00 | 17:00 |  |  | 74