## Project Schedule
| WBS | Task Name | Duration | Start | Finish | Predecessors | % Complete | JM | Quantiry
1 | 1 | General Civil Works | 75 days | Mon 10/16/17 8:00 AM | Wed 12/27/17 5:00 PM |  | 0%
2 | 1.1 | Site Levelling and Grading | 10 days | Mon 10/16/17 8:00 AM | Fri 10/27/17 5:00 PM |  | 100%
3 | 1.2 | Marking of Boundary Wall | 3 days | Wed 11/1/17 8:00 AM | Fri 11/3/17 5:00 PM |  | 100%
4 | 1.2 | Construction of Boundary Wall | 10 days | Sat 11/4/17 8:00 AM | Mon 11/13/17 5:00 PM | 3 | 0% | Location, , Markings, Dimensions for Foundation, Height and Width of the Walls, Type of Material
5 | 1.4 | Installation of Main Entry Gate | 3 days | Tue 11/14/17 8:00 AM | Thu 11/16/17 5:00 PM | 4 | 0%
6 | 1.6 | Construction of Security Cabin | 5 days | Fri 11/17/17 8:00 AM | Tue 11/21/17 5:00 PM | 5 | 0% | Location, , Markings, Dimensions for foundation,LBH of the Cabin, Type of Material
7 | 1.7 | Construction of Internal Roads | 30 days | Thu 11/16/17 8:00 AM | Wed 12/27/17 5:00 PM |  | 0% | Location, , Markings,Length, width of Road, Type of Material
8 | 1.8 | Construction of Drainage system | 30 days | Sat 11/18/17 8:00 AM | Sun 12/17/17 5:00 PM | 7SS+2 days | 0%
9 | 1.9 | Construction of Water Collection Tank | 15 days | Fri 12/1/17 8:00 AM | Thu 12/21/17 5:00 PM |  | 0% | Location, dimension for watertank, Type of Tank, Capacity of tank
10 | 1.1 | Borewell works | 1 day | Mon 10/16/17 8:00 AM | Mon 10/16/17 5:00 PM | 2SS | 100%
11 | 1.11 | Closed Storage Shed Construction | 2 days | Thu 10/26/17 8:00 AM | Fri 10/27/17 5:00 PM | 2SS+10 days | 0%
12 | 1.12 | Site Office Construction | 2 days | Thu 10/26/17 8:00 AM | Fri 10/27/17 5:00 PM | 2SS+10 days | 0% | Location, Markings, Dimensions for foundation,LBH of the Cabins, Type of Material
13 | 2 | Phase 1 | 1 day? | Mon 10/16/17 8:00 AM | Mon 10/16/17 5:00 PM |  | 1%
14 | 2.1 | Civil Works for Rooms | 26 days | Thu 10/26/17 8:00 AM | Mon 11/20/17 5:00 PM |  | 13%
15 | 2.1.1 | Inverter Room 1 | 26 days | Thu 10/26/17 8:00 AM | Mon 11/20/17 5:00 PM |  | 29%
16 | 2.1.1.1 | Marking and excavation | 2 days | Thu 10/26/17 8:00 AM | Fri 10/27/17 5:00 PM |  | 100% | Location, Alignment, Leveling, dimensions for excavation
17 | 2.1.1.2 | PCC and Rebar Assembly for columns | 3 days | Fri 10/27/17 8:00 AM | Tue 10/31/17 5:00 PM | 16 | 100%
18 | 2.1.1.3 | Concrete upto plinth level | 1 day | Wed 11/1/17 8:00 AM | Wed 11/1/17 5:00 PM | 17 | 100%
19 | 2.1.1.4 | Shuttering rod bending and concrete for plinth beams | 2 days | Thu 11/2/17 8:00 AM | Fri 11/3/17 5:00 PM | 18 | 100%
20 | 2.1.1.5 | Raising columns upto slab beam level | 3 days | Fri 11/3/17 8:00 AM | Sun 11/5/17 5:00 PM | 19 | 50% | Width of the coloum, material requirement
21 | 2.1.1.6 | Shuttering rebar rod bending for beams | 3 days | Mon 11/6/17 8:00 AM | Wed 11/8/17 5:00 PM | 20 | 0%
22 | 2.1.1.7 | Roof Slab | 2 days | Thu 11/9/17 8:00 AM | Fri 11/10/17 5:00 PM | 21 | 0%
23 | 2.1.1.8 | Cable Trenches inside room for placing inverter | 12 days | Sat 11/4/17 8:00 AM | Wed 11/15/17 5:00 PM | 19 | 0% | Cable trench Excavation
24 | 2.1.1.9 | Brick wall construction and inside plastering for the same | 5 days | Thu 11/16/17 8:00 AM | Mon 11/20/17 5:00 PM | 23 | 0% | Quality of bricks,Thickness of wall & laying of bricks with frogs upward,Mortar mix proportion,Plumb, line & level,Opening size & location,Interlocking of even courses at wall junctions,Concrete band/ provision of bars in partition wall,Sill level & sill concrete,Lintel level
25 | 2.1.2 | Power Transformer-1 Foundation | 10 days | Sun 11/5/17 8:00 AM | Tue 11/14/17 5:00 PM | 16SS+10 days | 0% | Location, Marking, Excavation as per dimensions,
26 | 2.1.3 | Aux Transformer- Foundation | 10 days | Sun 11/5/17 8:00 AM | Tue 11/14/17 5:00 PM | 25SS | 0% | Location, Marking, Excavation as per dimensions( Design),
27 | 2.1.4 | Foundation for HT Panel-1 | 10 days | Wed 11/8/17 8:00 AM | Fri 11/17/17 5:00 PM | 19FS+4 days | 0% | Location, Marking, Excavation as per dimensions( Design),
28 | 2.1.5 | Foundation for Main HT Panel | 11 days | Thu 11/9/17 8:00 AM | Sun 11/19/17 5:00 PM | 27SS+1 day | 0% | Location, Marking, Excavation as per dimensions( Design),
29 | 2.2 | Structure | 19 days | Sat 10/28/17 8:00 AM | Wed 11/15/17 5:00 PM |  | 35%
30 | 2.2.1 | Foundation Marking for Structures | 2 days | Sat 10/28/17 8:00 AM | Sun 10/29/17 5:00 PM | 2 | 50% | Location,Marking, Orientation, Coordinate as per drawing
31 | 2.2.2 | Holes Excavation for Structure Foundation | 3 days | Mon 10/30/17 8:00 AM | Wed 11/1/17 5:00 PM | 30 | 100%
32 | 2.2.3 | Delivery of Column Posts | 0 days | Mon 10/30/17 8:00 AM | Mon 10/30/17 8:00 AM |  | 100%
33 | 2.2.4 | Concrete Piling for MMS | 4 days | Tue 10/31/17 8:00 AM | Fri 11/3/17 5:00 PM | 32 31SS+1 day | 100%
34 | 2.2.5 | Delivery of Structure Material | 0 days | Fri 11/3/17 8:00 AM | Fri 11/3/17 8:00 AM |  | 100%
35 | 2.2.6 | Structure Erection | 6 days | Sun 11/5/17 8:00 AM | Fri 11/10/17 5:00 PM | 34 33FS+1 day | 0% | Drawings For erection, Availablity of material, Alignment, levels, location, orientations
36 | 2.2.7 | Foundation Coping for Structure | 2 days | Sat 11/11/17 8:00 AM | Sun 11/12/17 5:00 PM | 35 | 0%
37 | 2.2.8 | Delivery of PV Modules | 0 days | Fri 11/10/17 8:00 AM | Fri 11/10/17 8:00 AM |  | 0%
38 | 2.2.9 | Installation of PV Module | 4 days | Fri 11/10/17 8:00 AM | Mon 11/13/17 5:00 PM | 35SS+3 days 37 | 0% | Type,Make, Wattage of Madule( As per control Drawing/BOQ), Module Mounting( No Mixing of different wattage of module within string), Use correct Clamp(AS per Drawing), Gap B/W to Modules(Should be equal to the width of the clamp or as per drawing), Tightening of fasteners of Module Clamp(Should be with appropriate torque of value 12 to 16 N/m2), Grounding of Modules, Module should be grounded (sample testing of Module Grounding to be carried out),RFID Tag fixing(if required) | 22480
39 | 2.2.10 | Handing over of Structures and Modules | 2 days | Tue 11/14/17 8:00 AM | Wed 11/15/17 5:00 PM | 38 | 0%
40 | 2.3 | DC Side Activities | 16 days | Tue 11/7/17 8:00 AM | Wed 11/22/17 5:00 PM |  | 0%
41 | 2.3.1 | Erection of String Monitoring Boxes | 6 days | Mon 11/13/17 8:00 AM | Sat 11/18/17 5:00 PM | 38SS+3 days | 0%
42 | 2.3.2 | Laying of 6 mm DC Cable & Module Stringing | 8 days | Wed 11/15/17 8:00 AM | Wed 11/22/17 5:00 PM | 41SS+2 days | 0% | Type of cable as per SLD/BOQ, Insulation Resistance,
43 | 2.3.3 | Cable trench Opened | 6 days | Tue 11/7/17 8:00 AM | Sun 11/12/17 5:00 PM | 35SS+2 days | 0% | excavation as per design,
44 | 2.3.4 | Laying of DC Cable from SMB to Inverter | 8 days | Mon 11/13/17 8:00 AM | Mon 11/20/17 5:00 PM | 41SS | 0% | Length of the cable,
45 | 2.3.5 | Cable trench Closed | 2 days | Tue 11/21/17 8:00 AM | Wed 11/22/17 5:00 PM | 44 | 0%
46 | 2.3.6 | Installation of Lightening Arrestor | 2 days | Sat 11/11/17 8:00 AM | Sun 11/12/17 5:00 PM | 35 | 0% | Type, Make, Capacity as per Design,
47 | 2.3.7 | Earth Pit Works | 2 days | Sat 11/11/17 8:00 AM | Sun 11/12/17 5:00 PM | 35 | 0% | Location, Earth pit excavation as per design, Distance between earth pits, Soil Filling
48 | 2.3.8 | DC Earthing | 7 days | Sat 11/11/17 8:00 AM | Fri 11/17/17 5:00 PM | 35 | 0% | Earth pit prepararion, Distance b/w two earth pits,Earth pit mesh, earth strip size
49 | 2.4 | Plant AC Works | 22 days | Wed 11/1/17 8:00 AM | Wed 11/22/17 5:00 PM |  | 0%
50 | 2.4.1 | Inverters Installation | 3 days | Mon 11/20/17 8:00 AM | Wed 11/22/17 5:00 PM |  | 0%
51 | 2.4.1.1 | Placing of Inverters | 1 day | Tue 11/21/17 8:00 AM | Tue 11/21/17 5:00 PM | 24 | 0%
52 | 2.4.1.2 | Inverter AC Side Terminations | 1 day | Mon 11/20/17 8:00 AM | Mon 11/20/17 5:00 PM | 63 | 0%
53 | 2.4.1.3 | Inverter DC Side Terminations | 1 day | Tue 11/21/17 8:00 AM | Tue 11/21/17 5:00 PM | 44 | 0%
54 | 2.4.1.4 | Inverter Installation | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 52 53 | 0%
55 | 2.4.2 | Installation of HT Panels | 3 days | Mon 11/20/17 8:00 AM | Wed 11/22/17 5:00 PM |  | 0%
56 | 2.4.2.1 | Main HT Panel Installation | 2 days | Tue 11/21/17 8:00 AM | Wed 11/22/17 5:00 PM | 28FS+1 day | 0%
57 | 2.4.2.2 | HT Panel-1 Installation | 2 days | Mon 11/20/17 8:00 AM | Tue 11/21/17 5:00 PM | 27FS+2 days | 0%
58 | 2.4.3 | Transformers(Power and Aux.) | 2 days | Fri 11/17/17 8:00 AM | Sat 11/18/17 5:00 PM |  | 0%
59 | 2.4.3.1 | Installation of Power Transformer -1 | 2 days | Fri 11/17/17 8:00 AM | Sat 11/18/17 5:00 PM | 25FS+2 days | 0% | Type, Make, Capacity as per Design,
60 | 2.4.3.2 | Installation of Aux Transformer | 2 days | Fri 11/17/17 8:00 AM | Sat 11/18/17 5:00 PM | 26FS+2 days | 0% | Type, Make, Capacity as per Design,
61 | 2.4.4 | AC Cabling | 6 days | Thu 11/16/17 8:00 AM | Tue 11/21/17 5:00 PM |  | 0%
62 | 2.4.4.1 | AC Cable trenches | 4 days | Thu 11/16/17 8:00 AM | Sun 11/19/17 5:00 PM | 16 | 0% | Location, Marking, Excavation for trench
63 | 2.4.4.2 | Laying & Termination of LT Cable Ivt-1 to T/f-1 | 2 days | Sat 11/18/17 8:00 AM | Sun 11/19/17 5:00 PM | 62SS+2 days | 0%
64 | 2.4.4.3 | Laying & Termination of HT Panel-1 to T/f-1 | 1 day | Mon 11/20/17 8:00 AM | Mon 11/20/17 5:00 PM | 63 | 0%
65 | 2.4.4.4 | Laying & Termination of HT Panel-1 to Main HT Panel | 1 day | Tue 11/21/17 8:00 AM | Tue 11/21/17 5:00 PM | 64 | 0%
66 | 2.4.5 | Plant Switchyard | 11 days | Mon 11/6/17 8:00 AM | Thu 11/16/17 5:00 PM |  | 0%
67 | 2.4.5.1 | Marking of Switchyard | 1 day | Mon 11/6/17 8:00 AM | Mon 11/6/17 5:00 PM |  | 0% | Location, Leveling, marking as per design
68 | 2.4.5.2 | Plant Switchyard Material Delivery | 0 days | Mon 11/6/17 8:00 AM | Mon 11/6/17 8:00 AM |  | 0%
69 | 2.4.5.3 | Switch Yard CT Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0% | Location,Marking, Excavation as per design
70 | 2.4.5.4 | Switch Yard PT Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0%
71 | 2.4.5.5 | Switch Yard Isolator Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0%
72 | 2.4.5.6 | Switch Yard Breaker Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0%
73 | 2.4.5.7 | Switch Yard Tower Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0%
74 | 2.4.5.8 | Switch Yard Earthing Connections | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 67 | 0%
75 | 2.4.5.9 | Installation of CT | 2 days | Thu 11/9/17 8:00 AM | Fri 11/10/17 5:00 PM | 69 68 | 0% | Type, Make, Rating as per Design,
76 | 2.4.5.10 | Installation of PT | 2 days | Thu 11/9/17 8:00 AM | Fri 11/10/17 5:00 PM | 70 68 | 0% | Type, Make, Rating as per Design,
77 | 2.4.5.11 | Installation of Isolator | 2 days | Thu 11/9/17 8:00 AM | Fri 11/10/17 5:00 PM | 71 68 | 0% | Type, Make, Rating as per Design,
78 | 2.4.5.12 | Installation of Breaker | 2 days | Thu 11/9/17 8:00 AM | Fri 11/10/17 5:00 PM | 72 68 | 0% | Type, Make, Rating as per Design,
79 | 2.4.5.13 | Switch Yard Earthing Mat Construction | 2 days | Sat 11/11/17 8:00 AM | Sun 11/12/17 5:00 PM | 76 77 78 | 0%
80 | 2.4.5.14 | Termination of Conductors | 2 days | Mon 11/13/17 8:00 AM | Tue 11/14/17 5:00 PM | 79 | 0%
81 | 2.4.5.15 | Finishing of plant switchyard | 2 days | Wed 11/15/17 8:00 AM | Thu 11/16/17 5:00 PM | 80 | 0%
82 | 2.4.6 | Bay Switchyard | 15 days | Mon 11/6/17 8:00 AM | Mon 11/20/17 5:00 PM | 67SS | 0%
83 | 2.4.6.1 | Bay Switchyard Material Delivery | 1 day | Mon 11/6/17 8:00 AM | Mon 11/6/17 5:00 PM |  | 0%
84 | 2.4.6.2 | Bay Marking | 1 day | Mon 11/6/17 8:00 AM | Mon 11/6/17 5:00 PM | 67SS | 0%
85 | 2.4.6.3 | Bay CT Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 84 83 | 0%
86 | 2.4.6.4 | Bay PT Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 84 83 | 0%
87 | 2.4.6.5 | Bay Isolator Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 84 83 | 0%
88 | 2.4.6.6 | Bay Breaker Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 84 83 | 0%
89 | 2.4.6.7 | Bay Tower Foundation | 2 days | Tue 11/7/17 8:00 AM | Wed 11/8/17 5:00 PM | 84 83 | 0%
90 | 2.4.6.8 | Installation of CT | 3 days | Thu 11/9/17 8:00 AM | Sat 11/11/17 5:00 PM | 85 | 0% | Type, Make, Rating as per Design,
91 | 2.4.6.9 | Installation of PT | 3 days | Thu 11/9/17 8:00 AM | Sat 11/11/17 5:00 PM | 86 | 0% | Type, Make, Rating as per Design,
92 | 2.4.6.10 | Installation of Isolator | 3 days | Thu 11/9/17 8:00 AM | Sat 11/11/17 5:00 PM | 87 | 0% | Type, Make, Rating as per Design,
93 | 2.4.6.11 | Installation of Breaker | 3 days | Thu 11/9/17 8:00 AM | Sat 11/11/17 5:00 PM | 88 | 0% | Type, Make, Rating as per Design,
94 | 2.4.6.12 | Termination of Conductors | 3 days | Sun 11/12/17 8:00 AM | Tue 11/14/17 5:00 PM | 90 91 92 93 | 0%
95 | 2.4.6.13 | Bay Earthing | 3 days | Wed 11/15/17 8:00 AM | Fri 11/17/17 5:00 PM | 94 | 0%
96 | 2.4.6.14 | Finishing of bay switchyard | 3 days | Sat 11/18/17 8:00 AM | Mon 11/20/17 5:00 PM | 95 | 0%
97 | 2.4.7 | Transmission Line | 19 days | Wed 11/1/17 8:00 AM | Sun 11/19/17 5:00 PM |  | 0%
98 | 2.4.7.1 | Transmission Line pole erection | 17 days | Wed 11/1/17 8:00 AM | Fri 11/17/17 5:00 PM |  | 0% | Location, dimesions of digging, Depth of the digging, concrete mixture, Pole Dimensions, Type of Pole, Height of the pole, Manufacturing details
99 | 2.4.7.2 | Delivery of Conductor Material | 1 day | Sat 11/11/17 8:00 AM | Sat 11/11/17 5:00 PM |  | 0% | Checking quantity of material
100 | 2.4.7.3 | Erection of Materials Ex: X -Arm Insulators Clamps | 5 days | Wed 11/15/17 8:00 AM | Sun 11/19/17 5:00 PM | 98SS+14 days 99FS+3 days | 0% | Dimensions of Material
101 | 2.4.7.4 | Stringing of Conductor | 5 days | Wed 11/15/17 8:00 AM | Sun 11/19/17 5:00 PM | 98SS+14 days 99FS+3 days | 0% | Size of conductor, Diameter of conductor, No of Strands, Each Strand Diameter,length of the span
102 | 2.4.8 | Earthing Check | 2 days | Tue 11/21/17 8:00 AM | Wed 11/22/17 5:00 PM | 50FS-2 days 55FS-2 days 58FS-2 days 91FS-2 days 99FS-2 days 82FS-2 days 97FS-2 days | 0% | Place of Earthing, Diameter of Earth Wire, Proper connection or not
103 | 2.5 | Miscellaneous Activities | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM |  | 0%
104 | 2.5.1 | Installation and Termination of LT Panels Inv Room 1 | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 | 0%
105 | 2.5.2 | Laying & Termination Control Cable Inverter Room 1 | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 | 0%
106 | 2.5.3 | Installation of Battery Bank Inverter Room -1 | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 | 0%
107 | 2.5.4 | Installation and Termination of Lighting System Inverter Room-1 | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 | 0%
108 | 2.5.5 | Installation and Termination of Misc.Items Inverter Room-1 | 1 day | Wed 11/22/17 8:00 AM | Wed 11/22/17 5:00 PM | 51 | 0%
109 | 2.6 | Testing and commissioning | 3 days | Thu 11/23/17 8:00 AM | Sat 11/25/17 5:00 PM |  | 0%
110 | 2.6.1 | Inspection of Plant | 1 day | Thu 11/23/17 8:00 AM | Thu 11/23/17 5:00 PM | 40 49 103 | 0%
111 | 2.6.2 | Trial Run | 1 day | Thu 11/23/17 8:00 AM | Thu 11/23/17 5:00 PM | 40 49 103 | 0%
112 | 2.6.3 | CEIG Inspection & Rectifications | 2 days | Thu 11/23/17 8:00 AM | Fri 11/24/17 5:00 PM | 40 49 103 | 0%
113 | 2.6.4 | Precommissioning | 1 day | Thu 11/23/17 8:00 AM | Thu 11/23/17 5:00 PM | 40 49 103 | 0%
114 | 2.6.5 | Grid Connection | 1 day | Thu 11/23/17 8:00 AM | Thu 11/23/17 5:00 PM | 40 49 103 | 0%
115 | 2.6.6 | Commissioning | 1 day | Sat 11/25/17 8:00 AM | Sat 11/25/17 5:00 PM | 112 114 | 0%
116 | 3 | Phase 2 | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
117 | 3.1 | Civil Works for Rooms | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
118 | 3.1.1 | Inverter Room 2 | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
119 | 3.1.1.1 | Marking and excavation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
120 | 3.1.1.2 | PCC and Rebar Assembly for columns | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
121 | 3.1.1.3 | Concrete upto plinth level | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
122 | 3.1.1.4 | Shuttering rod bending and concrete for plinth beams | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
123 | 3.1.1.5 | Raising columns upto slab beam level | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
124 | 3.1.1.6 | Shuttering rebar rod bending for beams | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
125 | 3.1.1.7 | Roof Slab | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
126 | 3.1.1.8 | Cable Trenches inside room for placing inverter | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
127 | 3.1.1.9 | Brick wall construction and inside plastering for the same | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
128 | 3.1.2 | Main Control Room | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
129 | 3.1.2.1 | Marking and excavation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
130 | 3.1.2.2 | PCC and Rebar Assembly for columns | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
131 | 3.1.2.3 | Concrete upto plinth level | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
132 | 3.1.2.4 | Shuttering rod bending and concrete for plinth beams | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
133 | 3.1.2.5 | Raising columns upto slab beam level | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
134 | 3.1.2.6 | Shuttering rebar rod bending for beams | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
135 | 3.1.2.7 | Roof Slab | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
136 | 3.1.2.8 | Cable Trenches inside room for placing inverter | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
137 | 3.1.2.9 | Brick wall construction and inside plastering for the same | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
138 | 3.1.3 | Power Transformer-2 Foundation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
139 | 3.1.4 | Power Transformer-3 Foundation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
140 | 3.2 | Structure | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
141 | 3.2.1 | Foundation Marking for Structures | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
142 | 3.2.2 | Holes Excavation for Structure Foundation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
143 | 3.2.3 | Delivery of Column Posts | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
144 | 3.2.4 | Concrete Piling for MMS | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
145 | 3.2.5 | Delivery of Structure Material | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
146 | 3.2.6 | Structure Erection | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
147 | 3.2.7 | Foundation Coping for Structure | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
148 | 3.2.8 | Installation of PV Module | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
149 | 3.2.9 | Handing over of Structures and Modules | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
150 | 3.3 | DC Side Activities | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
151 | 3.3.1 | Modules Connection | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
152 | 3.3.2 | String Monitoring Box Foundation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
153 | 3.3.3 | Placing of String Monitoring Box | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
154 | 3.3.4 | Laying of 6 mm DC Cable | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
155 | 3.3.5 | Terminations of SMB | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
156 | 3.3.6 | Cable trench Opened | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
157 | 3.3.7 | Laying of DC Cable from SMB to Inverter | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
158 | 3.3.8 | Cable trench Closed | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
159 | 3.3.9 | Lightening Arrester Foundations | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
160 | 3.3.10 | Installation of Lightening Arrestor | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
161 | 3.3.11 | Earth Pit Works | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
162 | 3.3.12 | Structure Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
163 | 3.3.13 | DC Earth Grid Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
164 | 3.3.14 | SMB Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
165 | 3.4 | Plant AC Works | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
166 | 3.4.1 | Inverters Installation | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
167 | 3.4.1.1 | Placing of Inverters | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
168 | 3.4.1.2 | Inverter AC Side Terminations | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
169 | 3.4.1.3 | Inverter DC Side Terminations | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
170 | 3.4.1.4 | Inverter Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
171 | 3.4.2 | Installation of HT Panels | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
172 | 3.4.2.1 | HT Panel -2 Installation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
173 | 3.4.2.2 | HT Panel-3 Installation | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
174 | 3.4.3 | Transformers(Power and Aux.) | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
175 | 3.4.3.1 | Installation of Power Transformer -2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
176 | 3.4.3.2 | Installation of Power Transformer -3 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
177 | 3.4.4 | AC Cabling | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
178 | 3.4.4.1 | AC Cable trenches | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
179 | 3.4.4.2 | Laying & Termination of LT Cable Ivt-2 to T/f-1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
180 | 3.4.4.3 | Laying & Termination of LT Cable Ivt-3 to T/f-1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
181 | 3.4.4.4 | Laying & Termination of LT Cable Ivt-4 to T/f-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
182 | 3.4.4.5 | Laying & Termination of LT Cable Ivt-5 to T/f-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
183 | 3.4.4.6 | Laying & Termination of LT Cable Ivt-6 to T/f-3 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
184 | 3.4.4.7 | Laying & Termination of LT Cable Ivt-7 to T/f-3 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
185 | 3.4.4.8 | Laying & Termination of HT Panel -2to T/f-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
186 | 6.5.11 | Laying & Termination of HT Panel -3to T/f-3 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
187 | 6.5.13 | Laying & Termination of HT Panel-2 to Main HT Panel | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
188 | 6.5.14 | Laying & Termination of HT Panel-3 to Main HT Panel | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
189 | 3.4.5 | Earthing | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
190 | 3.4.5.1 | DC earth pit Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
191 | 3.4.5.2 | AC earth pit Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
192 | 3.4.5.3 | LA Earthig Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
193 | 3.4.5.4 | AC earth Grid Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
194 | 3.4.5.5 | Inverter Room-2 Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
195 | 3.4.5.6 | Control Room Earthing | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
196 | 3.4.6 | Miscellaneous Activities | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
197 | 3.4.6.1 | Installation and Termination of Communication system | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
198 | 3.4.6.2 | Installation of CCTV | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
199 | 3.4.6.3 | Installation and Termination of SCADA | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
200 | 3.4.6.4 | Installation and Termination of Lighting System | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
201 | 3.4.6.5 | Installation and Termination of LT Panels Inv Room 1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
202 | 3.4.6.6 | Installation and Termination of LT Panels Inv Room 2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
203 | 3.4.6.7 | Installation and Termination of LT Panels MCR | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
204 | 3.4.6.8 | Laying & Termination Control Cable Inverter Room 1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
205 | 3.4.6.9 | Laying & Termination Control Cable Inverter Room 2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
206 | 3.4.6.10 | Laying & Termination Control Cable Main Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
207 | 3.4.6.11 | Installation of Battery Bank Inverter Room -1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
208 | 3.4.6.12 | Installation of Battery Bank Inverter Room -2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
209 | 3.4.6.13 | Installation of Battery Bank Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
210 | 3.4.6.14 | Installation and Termination of Lighting System Inverter Room-1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
211 | 3.4.6.15 | Installation and Termination of Lighting System Inverter Room-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
212 | 3.4.6.16 | Installation and Termination of Lighting System Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
213 | 3.4.6.17 | Installation and Termination of Misc.Items Inverter Room-1 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
214 | 3.4.6.18 | Installation and Termination of Misc.Items Inverter Room-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
215 | 3.4.6.19 | Installation and Termination of Misc.Items Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
216 | 3.4.6.20 | Installation of Weather Monitoring System | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
217 | 3.4.7 | Testing and commissioning | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
218 | 3.4.7.1 | Inspection of Plant | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
219 | 3.4.7.2 | Trial Run | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
220 | 3.4.7.3 | CEIG Inspection & Rectifications | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
221 | 3.4.7.4 | Precommissioning | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
222 | 3.4.7.5 | Commissioning | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
223 | 3.4.7.6 | Grid Connection | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
224 | 3.5 | Miscellaneous Activities | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
225 | 3.5.1 | Installation and Termination of Communication system | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
226 | 3.5.2 | Installation of CCTV | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
227 | 3.5.3 | Installation and Termination of SCADA | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
228 | 3.5.4 | Installation and Termination of Lighting System | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
229 | 3.5.5 | Installation and Termination of LT Panels Inv Room 2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
230 | 3.5.6 | Installation and Termination of LT Panels MCR | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
231 | 3.5.7 | Laying & Termination Control Cable Inverter Room 2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
232 | 3.5.8 | Laying & Termination Control Cable Main Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
233 | 3.5.9 | Installation of Battery Bank Inverter Room -2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
234 | 3.5.10 | Installation of Battery Bank Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
235 | 3.5.11 | Installation and Termination of Lighting System Inverter Room-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
236 | 3.5.12 | Installation and Termination of Lighting System Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
237 | 3.5.13 | Installation and Termination of Misc.Items Inverter Room-2 | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
238 | 3.5.14 | Installation and Termination of Misc.Items Control Room | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
239 | 3.5.15 | Installation of Weather Monitoring System | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
240 | 3.6 | Testing and commissioning | 1 day | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
241 | 3.6.1 | Inspection of Plant | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
242 | 3.6.2 | Trial Run | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
243 | 3.6.3 | CEIG Inspection & Rectifications | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
244 | 3.6.4 | Precommissioning | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
245 | 3.6.5 | Commissioning | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%
246 | 3.6.6 | Grid Connection | 1 day? | Sat 11/4/17 8:00 AM | Sat 11/4/17 5:00 PM |  | 0%